# Feasibility Study: Crossroads Community STEM Centre

An Assessment of the Viability of Establishing a Community STEM Learning Hub in Langford, British Columbia

Prepared for: Jasmine North, Department of English, Camosun College

Prepared by: Cameron Kibble, Founder, Crossroads Community Hub

Date: March 26, 2026 (Updated: March 29, 2026)

Table of Contents

Introduction

Needs Analysis

System Identification

Problem Formulation

Generation of System Alternatives

Determination of Viability

6.1 Technical Feasibility

6.2 Updated Cost Analysis - 2026 Adjustment

6.3 Revised Economic Feasibility

6.4 Social Feasibility

6.5 Environmental and Cultural Feasibility

6.6 Political and Legal Feasibility

6.7 Operational Feasibility

6.8 Schedule Feasibility

Conclusion and Recommendation

References

## 1. Introduction

This feasibility study assesses the viability of establishing the Crossroads Community STEM Centre, a proposed open-access technical learning facility in Langford, British Columbia. The study evaluates the project across technical, economic, social, environmental, political, and operational dimensions to determine whether the project should proceed to the funding acquisition and construction phases. All data presented herein is drawn from the Crossroads Community STEM Centre Project Proposal (March 2026), an independent 2026 local market cost analysis, and a community needs assessment survey conducted in February 2026.

## 2. Needs Analysis

Langford is Vancouver Island’s fastest-growing municipality, with a 2024 population of 58,320 and a 5.0 percent year-over-year growth rate. Despite this expansion, the West Shore region lacks a centralized, open-access facility where residents can develop practical technical skills outside of formal post-secondary enrollment. Access to advanced tools and lab environments in the Greater Victoria area is concentrated within institutions that impose tuition, enrollment, and scheduling barriers.

A review of existing alternatives in the region confirms this gap. The University of Victoria and Camosun College maintain well-equipped STEM labs, but access is restricted to enrolled students during designated institutional hours. The Victoria Makerspace operates on an application-based membership model with limited public drop-in hours and a club-oriented atmosphere focused on a narrow range of hobbyist disciplines.

A community needs assessment survey of 54 respondents in the Langford and Greater Victoria area yielded the following results:

78% identified “lack of affordable access to tools and lab space” as their primary barrier to developing technical skills.

65% indicated they would “definitely” or “probably” use a drop-in community STEM facility in Langford.

61% preferred a monthly membership fee in the $25 to $50 range, though market realities may necessitate adjustments.

The British Columbia Ministry of Education’s Applied Design, Skills, and Technologies (ADST) curriculum emphasizes experiential learning and iterative design across K-12 education. Crossroads directly extends the ADST model into the community setting, bridging the gap between secondary education and professional practice.

## 3. System Identification

The proposed system is a nonprofit community STEM learning facility located in Langford, BC, operating across four core disciplines: Robotics and Electronics, Digital Fabrication, Software Development, and Creative and Applied Design.

Exogenous Variables:

Municipal population growth rate and demographic shifts in the West Shore.

Langford commercial real estate market lease rates (Net + NNN).

Provincial and federal grant funding climate for educational nonprofits.

WorkSafeBC regulatory requirements and premium rates for workshop environments.

BC Societies Act requirements for nonprofit incorporation.

Inflationary pressures on specialized equipment and regional wage benchmarks.

Overt Variables:

Staffing model and compensation structure.

Equipment selection, lifecycle management, and procurement strategy.

Programming schedule spanning 73 total access hours.

Fee structure encompassing sliding-scale memberships, drop-in passes, and workshop fees.

Revenue diversification strategy capping single-source dependencies at 30%.

## 4. Problem Formulation

Langford, BC, despite its rapid demographic and economic expansion, lacks an open-access community facility for residents to develop practical STEM skills using professional-grade equipment without post-secondary enrollment. Existing alternatives either restrict access to enrolled students or impose application-based membership barriers unsuited to beginners. Consequently, career changers, youth exploring STEM interests, and local professionals lack affordable, structured access to hands-on technical education.

## 5. Generation of System Alternatives

Three system alternatives have been developed to address the problem formulation, representing different risk and investment profiles.

Alternative A - Lean Model (4,000 sqft): Focuses on core equipment clusters in 3D printing, electronics, and computing. Requires two full-time safety instructors for 63 staffed hours per week. This model prioritizes manageable capital risk and operational agility.

Alternative B - Expanded Model (6,000 sqft): Includes a full equipment complement, adding a larger CNC router, expanded fabrication lab, and dedicated enterprise-grade digital infrastructure. Maximizes service capacity but requires substantially higher initial capital and staffing overhead.

Alternative C - Pop-Up Fallback Model: A mobile workshop model renting existing community center space for targeted, schedule-bound programming. This functions purely as a risk-mitigation fallback if permanent facility acquisition is severely delayed, as it cannot deliver the continuous equipment access fundamental to the project’s core mission.

Comparison: Alternative A is recommended for initial launch. It carries a lower financial risk profile and can sustainably scale to Alternative B as earned revenue stabilizes.

## 6. Determination of Viability

### 6.1 Technical Feasibility

The required equipment is commercially available and well-documented. Specific acquisitions include standard FDM 3D printers, a 40W CO2 laser cutter, benchtop CNC routers, and standard electronics testing hardware. The facility requires 200-amp electrical service, industrial ventilation for fabrication areas, and compliance with the Accessible Canada Act. These requirements are standard for light industrial spaces available in Langford’s McCallum Road and West Shore Parkway zones. WorkSafeBC guidelines are satisfied through a mandatory safety orientation and dual-supervisor coverage during high-risk equipment operation. Technical feasibility is confirmed.

### 6.2 Updated Cost Analysis - 2026 Adjustment

An independent analysis of Langford, British Columbia’s 2026 economic conditions necessitates an adjustment of the original March 2026 startup estimates. Inflationary pressures in the West Shore commercial real estate market and provincial wage adjustments require a recalibration of initial assumptions.

Cost Adjustments and Identifications:

Underestimated Costs: Initial personnel costs ($110,000 for 2 FTEs + Admin) were sub-market for 2026. Retaining qualified, safety-certified technical instructors in BC requires competitive compensation (estimated $65,000/year per Lead Instructor) plus a 15-20% load for mandatory benefits (WorkSafeBC premiums, CPP, EI). Furthermore, commercial lease estimates must be adjusted to $28-$30/sqft gross to accurately reflect recent municipal property tax impacts on Triple Net (NNN) leases.

Overestimated Costs: The initial $10,000-$20,000 marketing budget can be reduced. Organic community demand and strategic partnerships with local school districts will yield high initial conversion rates with a leaner digital marketing spend.

Missing Cost Categories: The original budget omitted an equipment depreciation/sinking fund and explicit accounting for commercial general liability (CGL) insurance riders specific to public-access high-risk machinery.

Table 1: 2026 Market Cost Adjustment Matrix (Startup & Year 1)

| Category | Initial Estimate (Lean) | 2026 Adjusted Reality (Lean) | Variance |
| --- | --- | --- | --- |
| Facility Operations (Lease + Utilities) | $96,000 | $120,000 | +25.0% |
| Personnel (Wages + Mandatory Benefits) | $110,000 | $165,000 | +50.0% |
| Equipment, Tooling, & Shipping | $60,000 | $68,000 | +13.3% |
| Legal, Permits, & High-Risk Insurance | $20,000 | $28,000 | +40.0% |
| Marketing & Outreach | $10,000 | $6,000 | -40.0% |
| Development Labor | $17,000 | $17,000 | 0.0% |
| Equipment Sinking Fund (New) | $0 | $10,000 | N/A |
| Contingency (15% of Subtotal) | $46,950 | $62,100 | +32.2% |
| Total Year 1 Capital Required | $359,950 | $476,100 | +32.2% |

### 6.3 Revised Economic Feasibility

The revised 2026 cost analysis confirms that the project remains economically viable, but the break-even threshold and revenue targets must be adjusted upward.

Table 2: Revised Annual Operating Costs (Ongoing)

| Cost Item | Lean Model (4,000 sqft) | Expanded Model (6,000 sqft) |
| --- | --- | --- |
| Facility Lease (Gross) & Utilities | $120,000 | $180,000 |
| Personnel (including Benefits) | $165,000 | $230,000 |
| Maintenance & Sinking Fund | $10,000 | $18,000 |
| Insurance, Operations & Legal | $15,000 | $22,000 |
| Total Annual Operating | $310,000 | $450,000 |

Break-Even Discussion & Revenue Assumptions:

Under the adjusted Lean Model, monthly operating expenses average approximately $25,833. To achieve a sustainable surplus for the contingency reserve, monthly revenue must target $29,000.

To meet this, the original membership pricing assumption must shift. The target becomes 200 active members at $60/month ($12,000), supported by $17,000 monthly distributed across workshop fees, corporate training contracts, institutional partnerships, and sustained grant funding. The commitment to capping any single funding source at 30% of total revenue remains intact, ensuring the center is shielded from abrupt grant cancellations.

Cost Sensitivity Analysis:

Best-Case Scenario: Equipment donations from institutional partners (e.g., Camosun College CTAC) offset up to $25,000 in capital expenditures; membership caps at 250 users, generating a comfortable monthly surplus.

Expected Scenario: Break-even is achieved in Month 8. Operating costs align with the $310,000 annual projection, requiring sustained baseline grant support alongside earned revenue.

Worst-Case Scenario: Commercial lease rates spike above $32/sqft or membership stalls below 120 users. The facility must immediately pivot to the Pop-Up Fallback Model to restrict overhead exposure while rebuilding community engagement.

### 6.4 Social Feasibility

Crossroads operates on a sliding-scale fee structure to ensure equitable access, mitigating the impact of the increased $60 base membership fee. Targeted outreach for low-income populations through partnerships with School Districts 61, 62, and 63 remains a priority. The volunteer mentorship cohort, projected at 15 to 25 active members, fosters a peer-support ecosystem, anchoring the facility as a vital “third place” for community development. Social feasibility remains highly robust.

### 6.5 Environmental and Cultural Feasibility

The project aligns cleanly with provincial initiatives promoting experiential, design-based learning. Light fabrication waste is managed via standard commercial protocols, and an emphasis is placed on iterative prototyping which inherently minimizes raw material waste. Culturally, the facility addresses the infrastructure deficit caused by rapid municipal expansion. Environmental and cultural feasibility is confirmed.

### 6.6 Political and Legal Feasibility

Incorporation as a nonprofit society under the BC Societies Act is required to maximize public trust and grant eligibility. The updated budget properly accounts for the comprehensive Commercial General Liability and specialized riders necessary for an open-access facility housing equipment like CO2 lasers and CNC mills. Political support for workforce readiness programs in the West Shore is strong. Political and legal feasibility is confirmed.

### 6.7 Operational Feasibility

The operational model relies on two full-time safety instructors working staggered shifts to cover 63 staffed hours per week, with an overlapping presence during peak afternoon and weekend hours. A mandatory safety orientation protocol complies with provincial health and safety mandates. Operational feasibility is confirmed.

### 6.8 Schedule Feasibility

A 12-month phased implementation timeline is maintained:

Months 1 to 3: Nonprofit incorporation and lease negotiation.

Months 4 to 6: Facility renovation and equipment commissioning.

Months 7 to 9: Soft launch, pilot workshops, and protocol testing.

Months 10 to 12: Full public launch and comprehensive evaluation.

Schedule feasibility is confirmed.

## 7. Conclusion and Recommendation

This feasibility study confirms that the Crossroads Community STEM Centre remains viable in the 2026 economic landscape. While regional market pressures in Langford, specifically commercial real estate rates and professional wage benchmarks, have increased the Year 1 Lean Model startup requirement to $476,100, the underlying demand for accessible technical education is thoroughly validated.

Recommendation: The project should immediately proceed to the funding acquisition phase utilizing the adjusted Lean Model (Alternative A). The revised operational budget of $310,000 annually is sustainable given the calculated break-even threshold of 200 members and diversified ancillary revenue streams. Execution should commence with the formalization of the nonprofit society and the initiation of targeted grant applications to secure the necessary startup capital.

## 8. References

[1] Statistics Canada, “Census profile, 2021 Census of Population: Langford, City [Census subdivision], British Columbia,” Government of Canada, Ottawa, ON, 2023.

[2] M. Rahman and M. Best, “Sustainability of makerspaces: Developing a framework for sustainable community innovation centers,” ACM Journal on Computing and Sustainable Societies, vol. 2, no. 3, art. 33, pp. 1-20, Sep. 2024.

[3] WorkSafeBC, “Education health and safety guidelines,” Richmond, BC, 2024.

[4] British Columbia Ministry of Education, “Applied design, skills, and technologies curriculum,” Victoria, BC, 2024.

[5] D. A. Kolb, Experiential Learning: Experience as the Source of Learning and Development, 2nd ed. Upper Saddle River, NJ: Pearson Education, 2015.

[6] A. Y. Kolb and D. A. Kolb, “Learning styles and learning spaces: Enhancing experiential learning in higher education,” Academy of Management Learning and Education, vol. 4, no. 2, pp. 193-212, Jun. 2005.

[7] R. Oldenburg, The Great Good Place: Cafes, Coffee Shops, Bookstores, Bars, Hair Salons, and Other Hangouts at the Heart of a Community, 3rd ed. New York, NY: Da Capo Press, 1999.

[8] D. Oblinger, Ed., Learning Spaces. Boulder, CO: EDUCAUSE, 2006.

[9] British Columbia Ministry of Education, “Student Learning Survey: Provincial results,” Victoria, BC, 2023.

[10] Council of Canadian Academies, “Some Assembly Required: STEM Skills and Canada’s Economic Productivity,” Ottawa, ON, 2015.

[11] Canada Not-for-profit Corporations Act, S.C. 2009, c. 23. Government of Canada, Ottawa, ON, 2009.

[12] Innovation, Science and Economic Development Canada, “SME Research and Statistics,” Government of Canada, Ottawa, ON, 2023.

[13] A. Cun, S. Abramovich, and J. M. Smith, “An assessment matrix for library makerspaces,” Library & Information Science Research, vol. 41, no. 1, pp. 39-47, 2019.